## Sheet1
Name | Start | Finish | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Project Proposal Document | Week 1 | Week 2 | 1 week
Proof of Stake/Work Research | Week 1 | Week 4 | 3 weeks
Design Proof of Stake Validation Approach | Week 3 | Week 4 | 1 week
Learn Golang | Week 1 | Week 4 | 3 weeks
Design Golang structs for nodes | Week 2 | Week 5 | 3 weeks
Requirements Specification | Week 3 | Week 5 | 2 weeks
Software Development Plan Document (Initial) | Week 3 | Week 5 | 2 weeks
Program Golang structs | Week 4 | Week 6 | 2 weeks
Software Development Plan Document (complete) | Week 3 | Week 7 | 4 weeks
Program Blockchain | Week 4 | Week 8 | 4 weeks
Program Peer-To-Peer model | Week 5 | Week 9 | 4 weeks
Software Design Description Document (Architecture) | Week 6 | Week 11 | 5 weeks
Project Critical Design Review Presentation | Week 9 | Week 12 | 3 weeks
Software Design Description Document (complete) | Week 9 | Week 12 | 3 weeks
Program Proof of Stake Validation | Week 5 | Week 13 | 8 week
Program Encryption | Week 10 | Week 13 | 3 weeks
ALPHA/BETA Presentation/Demonstration | Week 12 | Week 14 | 2 weeks
Test and Integration Plan | Week 11 | Week 14 | 3 weeks
User's Manual Final Updates | Week 6 | Week 15-16 | 9-10 weeks
FINAL Product Deliver (Final Report and Code) | Week 1 | Week 16
FINAL Project Presentation | Week 14 | Week 16
Oral Status Reports | Week 5 | Week 15 | Ongoing
Written Status Reports | Week 6 | Week 16 | Ongoing
Unit Tests | Week 4 | Week 16 | Ongoing